## B#28
BILL OF QUANTITIES AND THE ESTIMATE OF WORKS Bridge No.28 at km. 323+076.82 - bridge drainage
Pos. | Connection with techn. spec. | Description of the work | Unit of measure | Quantity | Unit price | Amount | Notes
3.2.1. |  | PREPARATION WORK
3.2.1.1. | 5.6.1.1 | Geodetic staking out of the route. Marking of the pipe route for rain sewage, the positions of the gutter outlets, and all pipe penetrations. | m1 | 12.4 |  | 0
TOTAL UNDER 3.2.1. | [5 empty] | 0
3.2.2. |  | EARTHWORKS
3.2.2.1. | 5.6.2.1 | Mechanical and manual excavation of trenches in materials of categories II and III for laying of sewer pipes. The width of the trench is variable depending on the diameter of the pipe. The corresponding width of the trench is given in the excavation tables. The depth of the trench is given in the longitudinal profiles. The excavation shall be performed in accordance with the technical drawings and instructions of the supervisory authority in accordance with the accompanying drawings. The excavation shall be carried out mechanically, except on sections where the route crosses with the installations of the PTT and EB lines, where the excavation will be carried out manually as well as fine planning. The sides of the trenches must be properly cut off, and the bottom of the trench is finely planned with a slope in the project. When excavating the ground, discard at least 1,0m from the edge of the trench. The excavation position is calculated on a table. Excavation is calculated from the area of the terrain as the road is designed in the embankment. It clings to m³ of excavated self-cultivated land depending on the depth of the trench.
|  | 0 - 2 m - Mechanical | m³ | 7.97 |  | 0
3.2.2.2. | 5.6.2 | Supply, transportation and placing the sand under the structure, bellow, next to and above the pipes. After placing the pipes on the bed, cover the pipes with the sand at least 10cm above the apex of pipes along the all width of a ditch except near joints. The payment is per m³ of placed sand. | m³ | 3.1 |  | 0
3.2.2.3. | 5.6.2.1 | Filling the trench with excavated material. After completing the sewage test, it is necessary to manually fill the trench. The filling should be performed using the excavated material. The price is determined per m³ of the material put into the trench | m³ | 4.87 |  | 0
3.2.2.4. | 5.6.2.2 | The disposal of surplus material to a landfill designated by the Supervisory Authority up to 5 km away. The price is determined per m³. | m³ | 2.8 |  | 0
TOTAL UNDER 3.2.2. | [5 empty] | 0
3.2.3. |  | INSTALLATION WORK
3.2.3.1 | 5.6.3.1 | The procurement, transport, and installation of sewage pipes made of hard polyester according to the HOBAS technology or similar. The pipes should be placed along the projected slope, and after the authorities have performed the technical acceptance of the built-in pipes, the trench should be filled and a hydraulic test should be performed.
|  | DN 160 mm | m1 | 57 |  | 0
3.2.3.2 | 5.6.3.1 | The purchase and installation of polyester fittings.
|  | Straight branches 160/110 | pcs. | 10 |  | 0
|  | Elbows L90 DN150 | pcs. | 9 |  | 0
|  | Elbows L45 DN150 | pcs. | 1 |  | 0
|  | EPDM couplings | pcs. | 10 |  | 0
|  | Rust pockets with an X-piece for DN 150 mm | pcs. | 2 |  | 0
3.2.3.2 | 5.6.3.1 | The purchase, transport and installation of mica flap DN 150 mm on the effluent of the pipe. | pcs. | 2 |  | 0
3.2.3.3. | 5.6.3.2 | Building pipe girders (pipe hangers). The price includes the manufacture and installation of underlay plates, screws, collars, and girders. The material is stainless steel. The price is determined for an installed set, depending on the pipe diameter and the type of hanger.
for DN 150 mm
|  | free girders | pcs. | 20 |  | 0
|  | fixed girders (longitudinal bracing) | pcs. | 6 |  | 0
TOTAL UNDER 3.2.3. | [5 empty] | 0
3.2.4. |  | CONCRETE WORKS
3.2.4.2. | 5.6.4 | Construction of drain heads of rainwater sewerage into inlets. The payment is per piece and it depends on pipe diameter. DN 200 mm. | pcs. | 1 |  | 0
TOTAL UNDER 3.2.4. | [5 empty] | 0
3.2.5. |  | OTHER WORK
3.2.5.1. | 5.6.5.3 | Rinsing the channel and removing all crude objects and dirt. The rinsing is done by means of water bowsers. | m1 | 57 |  | 0
3.2.5.2. | 5.6.5.1 | Testing the collector for leakage under hydraulic pressure. The collector is left under pressure until all parts of the collector (joints and pipes) are inspected. The collector should be checked according to the instructions provided. The price is determined per m1. | m1 | 57 |  | 0
3.2.5.3. | 5.6.5.2 | Recording the constructed pipeline. The price is determined per m1 | m1 | 57 |  | 0
3.2.5.4. | 5.6.5.4 | Analysis of the derived state. | lump sum
TOTAL UNDER 3.2.5. | [5 empty] | 0
TOTAL FOR THE COMPLETE WORK: | [5 empty] | 0 | €
NOTES: – All work listed in the bill of quantities is performed completely according to the graphic documentation from the Project as well as according to the Technical Specifications for performing the work provided in the Project.