#### Western Balkans Investment Framework Infrastructure Project Facility Technical Assistance 5 (IPF 5)

#### TA2015030 R0 IPA

Subproject: WB14-MNE-TRA-01

Reliability and Safety Improvement of “Bar-Vrbnica” Railway Line (SEETO Rail Route 4) – Phase 2                      Main Designs for Rehabilitation of 90 Concrete Bridges

#### Main Design for Rehabilitation of bridge No. 38 at km 330+649.90 of “Bar-Vrbnica” Railway

- Book 4 – Annexes

- Volume 4.2 – Study on the organization of traffic during the execution of works

- February 2018.

BOOK 4 – ANNEXES

VOLUME 4.2 – Study on the organization of traffic during the execution of works

Bridge no. 38 at km 330+649.90

________________________________________________

CONTENT OF VOLUME 4.2

1.	GENERAL DOCUMENTATION

1.1.	Contract

1.2.	Excerpt from the Central Registry for the company which made part of technical documentation

1.3.	Company license for preparing the part of the technical documentation

1.4.	Decision on appointment of Responsable Designer

1.5.	Licence of Responsable Designer and valid certificates of membership in IKCG

1.6.	Statement from the responsible designers that the technical documentation is made in accordance with the regulations ( Form 3 of the Rules )

1.7.	Liability insurance policy

2.	TEXTUAL DOCUMENTATION

1	TECHNICAL - EXPLOITATION CHARACTERISTICS OF VRBNICA – BAR RAILWAY

1.1	Basic data of the Vrbnica - Bar railway

1.2	Traffic on Vrbnica– Bar railway

1.2.1	Passenger traffic

1.2.2	Goods traffic

1.3	Vrbnica – Bar railway equipment with signal-safety devices

1.4	Contact network

2	Organization of works on the open railway and on the track at the station

2.1	Organization of works on the open railway and at the station area when the works are carried out under conditions of total suspension of train traffic

2.1.1	Closing the track outside the station area

2.1.2	Closing the track at the station

2.1.3	The additional requirements necessary for approval of the closure of the railway

2.2	Works while traffic is in progress

3	Safety measures related to work with and without the switching off voltage in the contact network

3.1	Procedure for disconnection of voltage in the contact line

3.2	Prohibited actions relating to the contact network

3.2.1	General prohibitions

3.2.2	Prohibited actions for carrying out works in the stations and on the open railway

4	ORGANIZATION OF RAILWAY TRAFFIC DURING THE EXECUTION OF WORKS

4.1	General principles

4.2	Measures of traffic organization

4.3	Shipping of a working train or TMD with material on a construction site on a track with traffic suspended

4.4	Speed of railway vehicles

4.5	The duties of the contractor and Railway Infrastructure of Montenegro

4.6	Other necessary conditions to be taken into account

5	The duties of individual workers in carrying out works on the railway

5.1	The duties of the manager of traffic operations

5.2	The duty of the security guard

5.3	The duties of the warning worker

5.4	The duty of engine drivers of trains with the works being performed under traffic with reduced speed

5.5	The duty of a leader and driver of the rail vehicle

5.6	Transport of workers

5.7	Safety time and safety distance

1	Bridge M40

1.1	Position of the bridge M40

1.2	Basic technical - exploitation characteristics of the bridge M40

1.3	Analysis of train traffic on bridges

2	Prescribed type and scope of works on the bridge M40

3	Location and security of construction site for the rehabilitation of the bridge M40

3.1	Works on selected bridges with the suspension of traffic and closure of railway

3.2	Works on selected bridges with permitted traffic with reduced train speeds (introduction of lightweight driving)

4	Conclusion

- EXECUTIVE SUMMARY IN ENGLISH ________________________________________________

CONTENT OF EXECUTIVE SUMMARY IN ENGLISH

EXECUTIVE SUMMARY IN ENGLISH ________________________________________________	4

1. Organization of open-air works and station areas	6

2. The procedure of disconnecting the voltage in the contact line	6

- 1. Organization of open-air works and station areas

Depending on the type and volume of the planned work on the track, it can be carried out in the conditions of complete rail-traffic suspension, i.e., with the railroad or railway track closed; or in the conditions of active train traffic, but with limited train speeds, i.e., the introduction of the, so called, "light rail" mode.

Planned work whose intervals are not foreseen in the general railway timetable is subsequently approved by the competent service of the Railway Infrastructure of Montenegro on the basis of a written request submitted by the work organization - contractor.

When submitting a request for the railway closure approval for planned track repair, all interested services participating in the execution of these works must be informed.

The operations manager hired by the company - contractor, on whose request the railway line closing is approved, is obliged to implement protective measures in order to secure the workplace on the railway (construction site).

If there are two or more construction sites between two adjacent stations, the execution of the work is regulated by a special instruction that includes the traffic of construction trains. The movement of construction vehicles, railway vehicles, and railroad machinery within the construction site, as well as between the construction sites, is regulated by the operations manager.

Building material and other equipment must not be disposed of in the niches. If this is necessary, then it is important to take this into account when determining the places where the workers will be sheltered if the arrival of the train is announced.

When work on the line has been completed, the operations manager shall notify the authorized persons of the Railway Infrastructure of Montenegro, who shall, on the basis of the work carried out, determine the conditions under which the traffic will take place after the railway track is reopened.

If it is necessary to close the track within the station for the purpose of carrying out work on the track, the approval for the closing of the track is given by the head of the station at the request of the contractor. All notified parties confirm the receipt of the approval to close the station track to the contractor who asked for the closing of the station track.

Regardless of whether the works are carried out when the railway (track) is closed or when trains are running with reduced speed (light rail), the authorized Infrastructure Manager and contractor employees are in charge of the correct installation of all signposts that protect the area of the construction site on the track ("STOP" shield, reduced speed signal, beginning and ending of light-rail mode, the "road works" signal sign, and the recall signal).

- 2. The procedure of disconnecting the voltage in the contact line

The work on the upper and lower structures is carried out without switching off the voltage in the train line, provided that the workers and tools handled by the workers do not exceed the danger zone. The danger zone extends at a distance of 2 m, measured from the most protruding part of the of the contact network that is under voltage, i.e., the range extends in the area of the track and the contact network lines at a height of 3 m above the upper edge of the rail.

When changing the rails, undertaking some other large-scale track and sleeper replacement, or carrying out the main repair or overhaul of the upper structure, the voltage in the contact line of such a track must be switched off and the train line earthed.

When the work on the railway line and the railway facilities requires the voltage in the contact network to be switched off and the contact network to be earthed, then the work must be secured by a team or an authorized maintenance worker. The contractor, i.e., the authorized employee of the Railway Infrastructure of Montenegro that the contractor contacts with, should inform the unit in charge of maintaining the contact network in a timely manner that there is a need for protecting the construction site. Based on this requirement, the contact network maintenance unit will duly send an authorized worker to perform the necessary voltage shut-down activities. The grounding of the train contact line at the construction site shall be carried out by an expert team of contractors, taking care not to damage any part of the contact network.