## M31 BoQ
THE ESTIMATE OF WORKS Bridge no. 31 at km 324+983.98
Pos. | Relation to techno. Spec. | Description of works | Meas. Unit | Quantity | Unit price | Amount | Notes
2.10. |  | PREPARATORY WORKS
2.10.01. | 2.10.1 | Formation of the building site. The building site is formed in a station Mojkovac (km 321+400). The transport of equipment, machinery and materials is from the station of Mojkovac to the bridge is executed by rail vehicles. | lump sum
2.10.02. |  | Geodetic tracing of the facility during the execution of rehabilitation works . | lump sum
2.10.03. |  | Conducting of the protective measures on work site during the execution of rehabilitation works. | lump sum
2.10.04. |  | Coordination of railway traffic during the execution of rehabilitation works . | lump sum
TOTAL FOR POS. 2.10. | [5 empty] | 0
2.20. |  | WORKS ON DEMOLITION AND DISMANTLING
2.20.01. | 2.20 | Controlled demolition of concrete of pedestrian paths (with the retaining of the existing reinforcement) and dismantling of the existing railing in the edge zone for the purpose of installation new cornice. The demolition is executed in the width of 25cm and the depth of ~8cm. The position of works comprises also the removal of non-bonded parts of concretein the lateral side of the existing cornice by abrasive methods, as well as the disposal of material on a landfill. | m' | 104.4 |  | 0
2.20.02. | 2.20 | Dismantling and removal of the existing expansion joints. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works (see Pos.2.140). | m' | 13.2 |  | 0
2.20.03. | 2.20 | Controlled demolition of concrete RC deck, parapet walls, walls, channel for installations walls and parapet wall of the basin of crushed stone surfacing, due to the embedding of new expansion joints. The demolition is executed in a full width of the traffic profile. The depth of demolition is conditioned by the sizes of new expansion joint. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140). | m' | 13.2 |  | 0
2.20.04. | 2.20 | The removal of the existing protective layer of waterproofing and waterproofing on the entire length of the bridge in a full profile due to installation of new waterproofing. This position of works comprises also. The works on the superstructure are not included in this position of works. (see Pos.2.140). | m2 | 269.77 |  | 0
2.20.05. | 2.20 | The removal of the existing gullies on the entire bridge length. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140). | pcs. | 20 |  | 0
2.20.06. | 2.20 2.151 | The removal of the existing tubules for dewatering of channels for installations of reparatory materials. This position of work comprises also the transport of removed material to a landfill, as well a the procurement and embedding of material for filling of the existing holes. | pcs. | 0 |  | 0
2.20.07. | 2.20 | The removal of the existing covers for installation channels on the entire bridge. This position of works comprises also the transport of removed covers to a landfill. | pcs. | 208 |  | 0
2.20.10. | 2.20 | Removal of large vegetation, stones and other obstacles from the round slope head and slopes in the intervention zone. The position of the work includes the transport of the removed material to the landfill, or its storage according to the instructions of the Supervisory Engineer. | m2 | 500 |  | 0
2.20.13. | 2.20 | Cleaning and putting into funkcion channel for receiving water from the slope, in the bridge zone. The position of the works include cleaning channels from soil, humus, rocks and other obstacles as well as their disposal to the landfill. | m' | 100 |  | 0
TOTAL FOR POS. 2.20. | [5 empty] | 0
2.30. |  | EARTHWORKS
2.30.05. | 2.30 | Works on stabilization of soil in piers zone, especially in the zone of pier S3. This position of the work implies bringing the terrain into the design state, stabilizing the slope and preventing further erosion. Works on this position include the removal of materials that are not suitable for compaction, pouring, tamping, leveling and landscaping. The position of the works includes the transport of the earth substance to the landfill. | m3 | 150 |  | 0
TOTAL FOR POS. 2.30. | [5 empty] | 0
2.40. |  | SCAFFOLDINGS, FORMWORKS AND TRANSPORT OF MATERIAL , PEOPLE AND EQUIPMENT
2.40.01. | 2.40 | Scaffolding and formwork: Scaffolding and formworks are not paid separately. The value of scaffolding and formwork is comprised by corresponding positions of works (through the unit prices ). | Given within the corresponding position of works
2.40.02. | 2.40 | Transport of material, people and equipment : Transport of material , people and equipment is not separately paid. the transport costs are comprised in the corresponding positions of works ( through the unit prices) | Given within the corresponding position of works
TOTAL FOR POS. 2.40.
2.50. |  | CONCRETING WORKS
2.50.01. | 2.50 | Making and mounting of prefabricated RC edge cornice on the right side of the bridge, concrete strength class C30/37, exposure class XC4; XD3; XF4. at the entire length of the bridge. | m3 | 3.12 |  | 0
2.50.02. | 2.50 | Making and mounting of the prefabricated RC lids (covers) for installation canals, of concrete of strength class C30/37, exposure class XC4; XD3; XF4. at the entire length of the bridge. | m3 | 3.432 |  | 0
2.50.03. | 2.50 | On-site concreting of the of the upper part of the edge cornice concrete strength class C30/37, exposure class XC4; XD3; XF4. This position also includes the filling of the holes, remaining after dismantling the existing fence of the pedestrian path. | m3 | 2.443 |  | 0
TOTAL FOR POS. 2.50. | [5 empty] | 0
2.60. |  | WORKS ON REINFORCEMENTS
2.60.01. | 2.60 | Procurement, bending, cutting and embedding of deformed bar reinforcement completely according to the details from The design. Quality of reinforcement B500B. | kg | 636.55 |  | 0
2.60.02. | 2.60 | Procurement, bending, cutting and embedding of smooth reinforcement completely according to the details from The design. Quality of reinforcement S240 (GA 240/360). | kg | 0 |  | 0
2.60.03. | 2.60 | Procurement, bending, cutting and embedding of mesh reinforcement completely according to the details from The design. Quality of reinforcement B500B. | kg | 385.49 |  | 0
TOTAL FOR POS. 2.60. | [5 empty] | 0
2.70. |  | METALLIC WORKS
2.70.01. | 2.70 | Procurement, making in the workshop, ACP, transport and mounting of two-sided pedestrian path on the span part of the bridge as well as onthe wing walls of the abutments. The minting of the fence is done by welding to the previously mounted steel plates (pos.2.150.06.). | m' | 104.4 |  | 0
2.70.02. | 2.70 | Procurement, making in the workshop, ACP, transport and mounting of steel gullies vertical elements Ø101.6mm length 70 cm. This position of works comprises also the workmanship and mounting of the protective steel caps of the gutters. The works on the superstructure are not included in this position of works (see Pos.2.140). | pcs. | 20 |  | 0
2.70.03. | 2.70 | Procurement of material, workmanship in the workshop, ACP, transport and mounting of the protective barriers on the bridge. The mounting of these barriers is executed by welding to the fence of the walkway. | m'
2.70.04. | 2.70 2.152 | Procurement of material, workmanship in the workshop, ACP and embedding of pipes Ø30mm, length 35 cm for dewatering of installation canals. These small tubules are placed in the previously prepared holes and after the execution of waterproofing of the installation canals. This position of works comprises also a drilling of holes for pipes Ø35mm, as well as the making and mounting of a steel cap, protective mesh and plastic extension Ø32mm length 14cm. | pcs. | 40 |  | 0
2.70.05. | 2.70 2.82 | Procurement of material, workmanship in the workshop, AKZ, transport and embedding of cover plates for the installation canals of corrugated sheet metal on the places of passing of expansion joints. This position of works comprises also the drilling of holes , procurement and embedding of anchor bolts for the fastening of corrugated sheet metal. | kg | 214.3 |  | 0 |  | `
TOTAL FOR POS. 2.70. | [5 empty] | 0
2.80. |  | WORKS ON REHABILITATION OF CONCRETE SURFACES
2.80.01. | 2.80 | Rehabilitation of the protective layer of concrete . The position of damage is presented in The imaging of damages - mark B.1. This position of works comprises the procurement, transport and embedding of reparative material. | m2 |  |  | 0
2.80.02. | 2.80 | Rehabilitation of segregated concrete zones. The position of damages is presented in The imaging of damages - mark B.2. This position comprises the procurement , transport and embedding of the reparative material. | m2 |  |  | 0
2.80.03. | 2.80 | Rehabilitation of mechanical damages of concrete. The damage positions are presented in The imaging of damages - mark B.3. This position comprises the procurement , transport and embedding of the reparative material. | dm3 |  |  | 0
2.80.04. | 2.80.7 | Rehabilitation of degraded concrete zones deeper than 5cm. The position of damages is presented in The imaging of damages - mark B.4. This position of works comprises the procurement , transport and embedding of reparative material. | m2 |  |  | 0
2.80.05. | 2.80.6 | Rehabilitation of degraded concrete zones from 0,5cm-5cm. The position of damage is presented in The imaging of damages - mark B.5. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 0.6 |  | 0
2.80.06. | 2.80 | Rehabilitation of surface degradations of concrete to 0,5cm. The position of damage is presented in The imaging of damages - mark B.6. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 0.2 |  | 0
2.80.07. | 2.80 | Rehabilitation of the zone of extension of concreting. The position of damage is presented in The imaging of damages - mark B.7. and B.8. This position of works comprises the procurement , transport and embedding of reparative material. | m' |  |  | 0
2.80.08. | 2.80 | Rehabilitation of calcified concrete zones. The position of damage is presented in The imaging of damages - mark B.9. and B.10. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 64 |  | 0
2.80.09. | 2.80.4 | Rehabilitation (injecting-grouting) of fissures to 3mm. The position of damage is presented in The imaging of damages - mark B.11. and B.13. This position of works comprises the procurement , transport and embedding of reparative material. | m' |  |  | 0
2.80.10. | 2.80.4 | Rehabilitation of fissures/cracks bigger than 3mm. The position of damage is presented in The imaging of damages - mark B.12. and B.14. This position of works comprises the procurement , transport and embedding of reparative material. | m' |  |  | 0
2.80.11. | 2.80 | Rehabilitation of mesh fissures. The position of damage is presented in The imaging of damages - mark B.15. and B.16. This position of works comprises the procurement , transport and embedding of reparative material. | m2 |  |  | 0
2.80.12. | 2.80 | Rehabilitation of badly executed local repairs of concrete . The position of damage is presented in The imaging of damages - mark B.17. and P.4. This position of works comprises the procurement , transport and embedding of reparative material. | pcs. |  |  | 0
2.80.14 | 2.80 | Rehabilitation of the upper surface of the roadway RC slab and vertical walls of the basin of crushed stone surfacing by reparative materials as a preparation of surfaces for the applying of the new insulation. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 269.77 |  | 0
2.80.15 | 2.80 | Rehabilitation of internal surfaces of the installation canals and making of sloping layer by reparative materials. This position comprises the procurement, transport and embedding of reparative material as well as the temporary local displacement of the installations. | m2 | 107.532 |  | 0
TOTAL FOR POS. 2.80. | [5 empty] | 0
2.90. |  | WORKS ON ANTI-CORRSION PROTECTION FOR STEEL
2.90.01. | 2.91 | ACP reinforcement on the places damages concrete surfaces. The position of damage is presented in The imaging of damages - mark A.1. and A.2. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 2 |  | 0
2.90.03. |  | Anti-corrosion protection of other steel elements is included within the positions of works under Pos.70. Metallic works.
TOTAL FOR POS. 2.90. | [5 empty] | 0
2.100. |  | WORKS ON THE WATERPROOFING
2.100.01. | 2.101.6 | Making of new waterproofing of RC deck. The waterproofing is executed on the entire bridge length in full profile with the special details of workmanship in the zone of gutter vertical elements, as well as on the vertical surfaces of crushed stone layer of basin. The position of works comprises the procurement, transport and embedding of waterproofing material. Rehabilitation of the upper surface of roadway RC slab and vertical walls of of the crushed stone basin is given separately in the position of works Pos.2.80.14. The works on the superstructure are not included in this position of works (see Pos.2.140). | m2 | 269.77 |  | 0
2.100.02. | 2.101.6 | Making of new waterproofing for installation channels. The waterproofing is executed on the entire length of the installation canals in a full profile with special workmanship detail in the zone of aligning surfaces of prefabricated RC cover plates. this position comprises the procurement , transport and embedding of waterproofing material , as well as the temporary displacement of installations. | m2 | 107.532 |  | 0
2.100.03. | 2.101.7 | Making of the waterproofing coating of walking surfaces of the walkways. The coating is executed also over the prefabricated RC cover plates for the installation canals. This position of works comprises the procurement, transport and embedding of waterproofing material. | m2 | 103.14 |  | 0
2.100.04. | 2.157 | Protection of waterproofing on vertical surfaces and protection of channels for installation from damages when installing ballast (crushed stone). Procurement, cutting and placement of panels of extruded polystyrene (styrofoam) 20mm thick. Calculation per m2 of surface protected by new waterproofing of the RC deck. | m2 | 269.77 |  | 0
TOTAL FOR POS. 2.100. | [5 empty] | 0
2.110. |  | EXPANSION JOINTS, POINTING AND BEARINGS
2.110.01. | 2.112 | Embedding of waterproof expansion joints. The selection of the manufacturer of dilatation coupler is executed by Contractor with an approval of Supervising body. This position comprises the procurement , transport and preparation of surfaces and embedding of a dilatation coupler. The demolition of concrete for the embedding of dilatation couplers is given separately in the position of works Pos.2.20.03. the works on the superstructure are not included in this position of works (see Pos.2.140).
2.110.01.1 |  | Capacity of dilatations ±22,5mm in the axis of abutment S1 | m' | 6.6 |  | 0
2.110.01.2 |  | Capacity of dilatations ±30,0mm in the axis of abutment S4 | m' | 6.6 |  | 0
TOTAL FOR POS. 2.110. | [5 empty] | 0
2.120. |  | DEWATERING
2.120.01. | 2.120 | Making of the closed dewatering system on the bridge, consisting of the gutter horizontal elements, vertical elements by the columns, collectors and separators. | Completely according to: Book 3 - Hydro technical design.
TOTAL FOR POS. 2.120.
2.130. |  | INSTALLATIONS AND POWEER SUPPLY GRID ON THE BRIDGE
2.130.01. | 2.153.1 | Removal of sand/gravel from the installation channels, and then the cleaning of canals by compressed air. The average thickness of sand/crushed stone that is being removed is 10cm. This position of works comprises also the transport of removed material to the landfill, and the temporary local displacement of the installations. | m3 | 4.698 |  | 0
2.130.02. | 2.130.1 | Procurement , transport and embedding of sand as the base / protection of the installations . Sand is embedded in two layers - the first layer 5cm thick as the base ( below) and the second layer 5 cm thick as the protection of the installations (above). The total thickness of sand is 10cm. This position comprises the temporary local removal of the installations. | m3 | 4.698 |  | 0
2.130.03. | 2.130.2 | Dismantling and repeated mounting of the existing cable for the grounding of the power grid overhead contact line (OCL) columnon the link with a rail. The bounding cable is joined to the rail by welding. | pcs. | 2 |  | 0
2.130.04. | 2.85 | Making of grout below the overhead contact line (OCL) column. The aligning size of steel panel on the joint of pylon for power grid is 60x60cm. This position comprises the procurement , transport and embedding of the material for undercuts. | pcs. | 2 |  | 0
2.130.05. | 2.71.3 2.82 | Replacement of bad/embedding of missing anchors bolts M30 of a necessary length on the joint of overhead contact line (OCL) column and RC cantilever. The position of these works comprises the procurement, transport and embedding of anchor bolts. | pcs. | 8 |  | 0
2.130.06. | 2.156 | Securing the workplace from the influence of voltage in the contact network. Immediately after switching off the current which is done by the ZICG, the expert team of the Contractor performs the grounding of the return circuit line on both sides of the bridge with the grounding rods. Calculation by m' of total dismantled track. | m' | 72.2 |  | 0
TOTAL FOR POS. 2.130. | [5 empty] | 0
2.140. |  | WORKS ON THE SUPERSTRUCTURE FOR THE PURPOSES OF REHABILITATION OF THE BRIDGE
2.140.02 | 2.140.02 | PROCUREMENT OF NEW IMPREGNATED BEECH SLEEPERS OF SIZE 16 x 26 x 260 cm. This position comprise the procurement and delivery to the construction site of new rail track sleepers according to EN13145 of size16 x 26 x 260cm. Calculation and payment per piece of delivered sleepers. | kom | 117 |  | 0
2.140.03-1 | 2.140.03-1 | PROCUREMENT OF NEW FASTENING ACCESSORY TYPE "K" FOR A WOODEN SLEEPER, DRIVING AND SAFETY RAILS 49E1 ON THE BRIDGE AND 3,00 m IN FRONT AND BEHIND THE BRIDGE. This position comprises the procurement and delivery to the construction site of the complete new fastening accessory type "K" for wooden sleepers and rails 49E1. One set contains: processed ribbed washer plate with the slope of 1:20 (ribbed plate + truncated ribbed plate ) - 2 pieces, fastening plate - 8 pcs, twofold elastic ring washer (Grower's ring) - 20 pieces, bolt of "T" shape together with a nut - 8 pieces, tirfon L=160 mm - 12 pcs, rubber insert - 4 pcs. The calculation and payment by a set of delivered fastening accessory per sleeper. | set | 93 |  | 0
2.140.03-2 | 2.140.03-2 | PROCUREMENT OF NEW FASTENING ACCESSORY TYPE "K" FOR WOODEN SLEEPER, DRIVING AND SAFETY RAIL 49E1 ON 7,0 m IN FRONT OF AND BEHIND THE BRIDGE . This position comprises the procurement and delivery to the construction site of the complete new fastening accessory type "K" for wooden sleepers and rails 49E1. One set contains: ribbed washer plate with slope - 4 pcs. fastening plate - 8 pcs. Twofold elastic ring washer (Grower's ring ) - 24 pcs. bolt of "T" shape with nuts - 8 pcs. tirfon L=160 mm - 16 pcs. rubber insert - 4 pcs. The calculation and payment for a set of delivered fastening accessory per sleeper. | set | 24 |  | 0
2.140.04 | 2.140.04 | PROCUREMENT, EXTERNAL TRANSPORT AND UNLOADING OF NEW CRUSHED STONE OF LIMESTONE ORIGIN. This position comprises the procurement, external transport and unloading on the place of embedding of crushed stone in Fed trolleys, with grain-size according to the standard for reception and delivery of crushed stone for the surfacing of railway lines. The calculation and payment for m3 of delivered crushed stone. | m³ | 177 |  | 0
2.140.05 | 2.140.05 | PROCUREMENT OF SETS FOR THE WELDING OF RAIL TRACK IN LRT OF 49E1 RAILS. This position comprises the procurement of all the necessary material for the making of welds on rail track made of 49E1 rails in LRT. The calculation and payment by a set. | komplet | 14 |  | 0
2.140.06 | 2.140.06 | PROCUREMENT OF UTENSILS AGAINST THE LONGITUDINAL RAIL DISPLACEMENTS . This position comprises the procurement and delivery of the utensils to the building site. The calculation and payment by a piece of delivered utensils.
|  | for wooden sleepers | kom | 148 |  | 0
2.140.07 | 2.140.07 | PROCUREMENT OF THE UTENSILS AGAINST THE LATERAL RAIL TRACK DISPLACEMENT. This position comprises the procurement and delivery of utensils on the building site.. The calculation and payment by a piece of delivered utensils.
|  | for wooden sleepers | kom | 59 |  | 0
2.140.09 | 2.140.09 | UNLOADING OF IMPREGNATD WOODEN SLEEPERS OF SIZE 16 x 26 x 260 cm. This position comprises the unloading of sleepers from trolleys, transfer to the construction site landfill and arrangement. The calculation and payment per piece of unloaded sleepers. | kom | 117 |  | 0
2.140.10 | 2.140.10 | UNLOADING OF TIGHTENING ACCESSORY TYPE „K“. This position comprises the unloading of rail track fastening accessory from trolleys with the transfer and arraigning in the construction site storeroom. The calculation and payment per ton of unloaded accessory. | t | 5.581 |  | 0
2.140.11 | 2.140.11 | UNLOADING OF UTENSILS AGAINST LONGITUDINAL RAIL DISPLACEMENTS. This position comprises an unloading of the utensils against a longitudinal rail displacement. The calculation and payment by a piece of unloaded utensils.. | kom | 148 |  | 0
2.140.12 | 2.140.12 | UNLOADING OF DEVICES AGAINST LATERAL TRACK RAIL DIPLACEMENTS. This position comprises an unloading of the utensils. The calculation and payment by a piece of unloaded utensils. | kom | 59 |  | 0
2.140.13 | 2.140.13 | DISMANTLING OF THE EXISTING RAIL TRACK . This position comprises a dismantling of the existing rail track, as well as the dismantling of the safety rails, with loading, transport to 10 km , unloading, dismantling and arranging by type and serviceability level. The calculation and payment by a km of dismantled rail track. | km | 0.07 |  | 0
2.140.13-1 | 2.140.13-1 | DISMANTLING OF THE EXISTING SAFETY RAIL. This position comprises a dismantling of the existing safety rail, as well as the dismantling of the safety rails, with loading, transport to 10 km, unloading and arranging by type and service ability level. The calculation and payment per m of dismantled safety rail. | m | 140 |  | 0
2.140.14 | 2.140.14 | REMOVAL OF THE EXISTING CRUSHED STONE SURFACING LAYER. This position comprises the complete cleaning and removal of the existing crushed stone surfacing layer with all accompanying works, below the rail track mesh on the bridge, to the existing railway slab of the bridge, with loading, transport to 10 km and unloading on the landfill. The calculation and payment by m3 of removed surfacing. | m³ | 147 |  | 0
2.140.15 | 2.140.15 | MOUNTING AND LAYING OF RAIL TRACK OF RAILS TYPE 49E1 ON WOODEN SLEEPERS. This position comprises the mounting and laying of rail track in front of and behind the bridge, on wooden sleepers, with the fastening accessory type "K". The calculation and payment by a km of the installed rail track. | km | 0.02 |  | 0
2.140.16 | 2.140.16 | MOUNTING AND LAYING OF THE RAIL TRACK OF RAILS TYPE 49E1 ON WOODEN SLEEPERS ON THE BRIDGE. This position comprises the mounting an laying of rail track on the bridge , on wooden sleepers, by a fastening accessory type "K". The calculation and payment by a km of mounted and installed rail track. . | km | 0.05 |  | 0
2.140.17 | 2.140.17 | MOUNTING OF SAFETY RAILS TYPE 49E1 ON WOODEN SLEEPERS. This position comprises the mounting of safety rails type 49E1 on wooden sleepers, with a fastening accessory type "K", with distortion on the ends and embedding of oak wedge. The calculation and payment by a km of mounted safety rail. | km | 0.07 |  | 0
2.140.22 | 2.140.22 | MECHANICAL ADJUSTMENT AND DYNAMIC STABILIZING OF RAIL TRACK OF RAILS TYPE 49E1. This position comprises the embedding of crushed stone in the rail track, raising of the rail track on the finished road level with a necessary camber and extensions in curvatures and under-compacting, mechanical regulating of the rail track by a direction and finished road level, fastening by proper accessory of rails type 49E1 with setting of the ballast prism (surfacing layer) and maintenance to the handover. The calculation and payment by a km of finally regulated rail track settled in the designed position. | km | 0.07 |  | 0
2.140.23 | 2.140.23 | WELDING OF RAIL TRACK OF RAILS TYPE 49E1 IN LRT BY AT PROCESS . This position comprises the welding of the rail track of rails type 49E1 in LRT by AT process, with the processing of welds and provisions of attests of the quality of welds. The calculation and payment by a weld. | var | 14 |  | 0
2.140.24 | 2.140.24 | RELEASE OF STRESS IN RAILS TYPE 49E1 WITH A FINAL WELDING. This position comprises the release of stress in the rails with a final welding according to The rulebook of the superstructure maintenance on the rail tracks. The calculation and payment by a km of released rail track. | km | 0.07 |  | 0
2.140.25 | 2.140.25 | EMBEDDING OF THE UTENSILS AGAINST A LONGITUDINAL RAIL DISPLACEMENT (MATHEE). This position comprises the embedding of utensils against a longitudinal rail displacement. The calculation and payment by a piece of the utensils. | kom | 148 |  | 0
2.140.26 | 2.140.26 | EMBEDDING OF UTENSILS AGAINST LATERAL RAIL DISPLACEMENT. This position comprises the embedding of utensils against lateral rail displacements. The calculation and payment by a piece of utensils. | kom | 59 |  | 0
2.140.27 | 2.140.27 | ADDITIONAL WORKS ON THE BRIDGE SUPERSTRUCTURE FOR THE EMBEDDING OF NEW WATERPROOFING, NEW GUTTER ELEMENTS AN DNEW BRIDGE DILATATIONS. This position comprises the necessary additional works on the bridge superstructure , such as: - cutting of the existing rail track in sections of 22,50 m, where a length on the embankment of 5,00m from the abutments ,in front of an behind the bridge, is taken into account; - dismantling of rail tracks in segments , with a temporary removal; - temporary mounting of the rail track , with drilling of rails , mounting of fastening links and necessary track accessory; - dismantling of rail content before welding of rails; This position comprises the procurement , transport and embedding of used elements for rails type 49E1. On complete consists of : link with rail type 49E1 for a joint - 2 pcs. bolt for joints M24 x 400 for one joint - 2 pcs. hexagonal nut for bolts for links M24 for one joint - 2 pcs. twofold elastic ring washer (Grower ring) - 2 pcs. The calculation and payment by a piece of joint. | kom | 10 |  | 0
2.140.28 | 2.140.28 | PROCUREMENT, TRANSPORT AND EMBEDDING OF NEW ADDITIONAL ACCESSORY FOR THE ENDS OF THE BRIDGE. This position comprises procurement and embedding of new additional accessory for ends of bridge, according to the provisions. One set consist of: oak insert 1 pcs.; tirfon L=150 mm - 2 pcs; tirfon L=160 mm - 1 pcs; joints (cur) - 2 pcs; bolts for joints M24 x 400 - 1 pcs; hexagonal nut fro bolts of joints M24 - 1 pcs. The calculation and payment per piece of placed additional accessory on the bridge ends. | komplet | 2 |  | 0
2.140.29 | 2.140.29 | PROCUREMENT, TRANSPORT AND EMBEDDING OF NEW ADDITIONAL ACCESSORY for JOINTS OF SAFETY RAILS ON THE BRIDGE. This position comprises the procurement and installation of new additional accessory for the joints of the safety rails on the bridge, completely according to the provisions. One set consists of: joints for rail type 49E1 for the joint of safety rails on the bridge - 2 pcs. bolt for joints M24 x 400 for one joint - 2 pcs. hexagonal nut for bolts M24 for one joint - 2 pcs. twofold elastic ring washer (Grower ring ) - 2 pcs. The calculation and payment per piece of joint. | kom | 10 |  | 0
2.140.30 | 2.140.30 | PROCUREMENT, EXTERNAL TRANSPORT AND UNLOAD OF NEW CUTTED OFF (ASLOPE) TIGHTENING PLATES This position comprises the procurement, external transport and unload at the installation site of new cutted off (aslope) tightening plates (standard P.B1.170), accessory type "K" for rails type 49E1. Cutted off tightening plates have shorter arm of tightening plates for 4mm. The installation was calculated through the position of the placement of rails. One set (complete) contains 4 tightening plates. The calculation and payment by a set of processed and embedded tightening plates. | set | 20 |  | 0
TOTAL FOR POS. 2.140. | [5 empty] | 0
2.150. |  | OTHER WORKS
2.150.02. | 2.80.10 | Applying of the protective coating on all visible concrete surfaces with the previous preparation of concrete surface by abrasive methods. The paint of the protective coating should be determined in agreement with The supervising body and The investor. This position of works comprises the procurement of material, transport and applying. Recommendation: SikaGard 680s or a coating with similar or better characteristics. | m2 | 1087.64 |  | 0
2.150.03. | 2.71 2.82 | Embedding of steel panels for the link of the fence of the walkway. Steel panels are linked to the structure through the anchor bolts M12,length 15cm,.4 pcs. This position comprises the procurement of the material , workmanship in the workshop, ACP, transport , drilling of holes Ø13mm and embedding of anchor bolts. | pcs. | 62 |  | 0
2.150.04 | 2.101.5 | Making of the protective coating on the basis of bitumen, for the protection of concrete surfaces of the strengthening of columns, that should be backfilled. | m2 | 50 |  | 0
2.150.10 | 2.153.2 | Removal of vegetation, from the round slope head of the bridge as well as in the wider zone around the bridge. | m2 | 98.1407 |  | 0
TOTAL FOR POS. 2.150. | [5 empty] | 0
2.160. |  | CONSULTING SERVICES
2.160.01. | 2.161 | The designer's supervision during the execution of works on the rehabilitation. Consulting services for the main project's modifications and supplements and the occasional presence on the facility to control the key positions of the works. The scope of engagement defines the Employer's Supervision according to real needs. | lump sum |  |  | 6000 | P.S.*
2.160.02. | 2.162 | The Investor's supervision during the execution of works on the rehabilitation. (N/A FIDIC Engineer defined in the Appendix to Tender) | lump sum |  |  | 0
2.160.03. | 2.164 | Creating As - Built Design (part of the Facility Maintenance Project) | lump sum
2.160.04. | 2.163 | Commission for the technical accept of the facility. | lump sum |  |  | 6800 | P.S.*
TOTAL FOR POS. 2.160. | [5 empty] | 12800
TOTAL WORKS FOR POS. 2.10 TO POS. 2.160 | [5 empty] | 12800
TOTAL FOR ALL THE WORKS : | [5 empty] | 12800 | €
NOTES: - All works mentioned in the estimate are executed completely according to the Graphic documentation from the Design, as well as the Technical specifications for the execution of works given in the Design. - Quantities Pos. 2.80. The works on the rehabilitation of concrete surfaces are given according to the Report on the state of the bridge from 2015 .
* P.S - To be paid as per Sub-Clause 13.5 - Provisional Sums
Note on C69: Predrag: waterproofing
Note on C83: Predrag: Installations and catenary system on the bridge
Note on C84: Predrag: Removal of sand/gravel from the installation channels