## M41 BoQ
THE ESTIMATE OF WORKS Bridge no. 41 at km 332+539.76
Pos. | Relation to techn. spec. | Description of works | Meas. Unit | Quantity | Unit price | Amount | Notes
2.10. |  | PREPARATORY WORKS
2.10.01. | 2.10.1 | Formation of the building site. The building site is formed in the station of Kolašin. | lump sum | 1
2.10.02. |  | Geodetic tracing of the facility during the execution of rehabilitation works . | lump sum | 1
2.10.03. |  | Conducting of the protective measures on work site during the execution of rehabilitation works. | lump sum | 1
2.10.04. |  | Coordination of railway traffic during the execution of rehabilitation works . | lump sum | 1
TOTAL FOR POS. 2.10. | [5 empty] | 0
2.20. |  | WORKS ON DEMOLITION AND DISMANTLING
2.20.01. | 2.20 | Controlled demolition of concrete of of pedestrian paths (with the retaining of the existing reinforcement) and dismantling of the existing railing in the edge zone for the purpose of installation new cornice. The demolition is executed in the width of 30cm and the depth of ~8cm. The position of works comprises also the removal of non-bonded parts of concretein the lateral side of the existing cornice by abrasive methods, as well as the disposal of material on a landfill. | m' | 40 |  | 0 | No new cornices are installed. Existing drip caps are in good condition, only disassembly of the fence is done.
2.20.02. | 2.20 | Dismantling and removal of the existing expansion joints. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works (see Pos.2.140). | m' | 10.8 |  | 0 | Dilatation achieved with "omega" sheet.
2.20.03. | 2.20 | Controlled demolition of concrete RC deck, parapet walls and channel for installations due to the embedding of new expansion joints. The demolition is executed in a full width of the traffic profile. The depth of demolition is conditioned by the sizes of new expansion joint. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140). | m' | 10.8 |  | 0
2.20.04. | 2.20 | The removal of the existing protective layer of waterproofing and waterproofing on the entire length of the bridge in a full profile due to installation of new waterproofing. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140). | m2 | 78.09 |  | 0
2.20.05. | 2.20 | The removal of the existing gullies on the entire bridge length. This position of works comprises also the transport of removed material to a landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140).. | kom. | 10 |  | 0
2.20.06. | 2.20 2.151 | The removal of the existing tubules for dewatering of channels for installations of reparatory materials. This position of work comprises also the transport of removed material to a landfill, as well a the procurement and embedding of material for filling of the existing holes. | kom. | 10 |  | 0
2.20.07. | 2.20 | The removal of the existing canal covers on the entire cover of the bridge. This position of works comprises also the transport of removed covers to a landfill. | kom. | 80 |  | 0
2.20.08. | 2.20 | Cleaning of the terrain in the bridge zone. This position comprises also the transport of material to a landfill. | pauš. | 1 |  | 0
2.20.09. | 2.20 | Controlled demolition of concrete of the interior walls of the installation channel for the installation of new parapets to secure the prism of the carriageway surfacing. The position of the works includes the removal of the demolished material to the landfill. The works on the superstructure are not included in this position of works. (see Pos.2.140). | m' | 40 |  | 0
TOTAL FOR POS. 2.20. | [5 empty] | 0
2.30. |  | EARTHWORKS
2.30.01. | 2.30 | The rehabilitation project does not envisage earth works | m3 | 0
TOTAL FOR POS. 2.30. | [5 empty] | 0
2.40. |  | SCAFFOLDINGS, FORMWORKS AND TRANSPORT OF MATERIAL , PEOPLE AND EQUIPMENT
2.40.01. | 2.40.1 | Scaffolding and formwork: Scaffolding and formworks are not paid separately. The value of scaffolding and formwork is comprised by corresponding positions of works (through the unit prices ). | Given within the corresponding position of works
2.40.02. | 2.40.2 | Transport of material , people and equipment : Transport of material , people and equipment is not separately paid. the transport costs are comprised in the corresponding positions of works ( through the unit prices) | Given within the corresponding position of works
TOTAL FOR POS. 2.40. | [5 empty] | 0
2.50. |  | CONCRETING WORKS
2.50.01. | 2.50 | Making and mounting of prefabricated RC edge cornice at the entire length of the bridge. The position includes the procurement of materials, transport, production in controlled conditions, transport to the construction site and installation. Installation includes welding of reinforcement for the existing reinforcement of the console. The dimension of elements are 50x49x6 cm. The reinforcement of prefabricated edge cornice is given by position 2.60.01. | m3 | 0 |  |  | No new edge cornices are installed. Existing drip caps are in good condition.
2.50.02 | 2.50 | Embedding of new concrete of edge cornice, strength class C30/37, exposure class XC4; XD3; XF4. New concrete is embedded at the entire length of the structure in a width of 36 cm and a thickness of 8 cm. The position of the works includes: filling the space between the prefabricated holder and console by repair mortar, preparation of a surface that involves coating with the old-new bond, material procurement, transportation, making and embedding. | m3 | 0 |  |  | No new edge cornicesare installed. Existing drip caps are in good condition.
2.50.03 | 2.50 | Making and mounting of the prefabricated RC lids (covers) for installation canals, of concrete of strength class C30/37, exposure class XC4; XD3; XF4. Covers are embedded at the entire length of the vault section of the bridge. The dimension of elements are 50x49x5 cm. The position includes the procurement of materials, transport, and production of covers. The reinforcement of covers is given by position 2.60.03 | m3 | 1 |  | 0
2.50.04 | 2.50 | Embedding of new C25/30 parapet concrete; XC4; XD3; XF4. New concrete is embedded at the entire length of the structure in a width of 15 cm and a height of 30 cm. The position of the works includes: preparation of the surface by coating the old - new bond, material procurement, transport, making and embedding. | m3 | 4.5 |  | 0
TOTAL FOR POS. 2.50. | [5 empty] | 0
2.60. |  | WORKS ON REINFORCEMENTS
2.60.01. | 2.60 | Procurement, bending, cutting and embedding of deformed bar reinforcement completely according to the details from The design for new edge cornice pos.2.50.01. Quality of reinforcement B500B. | kg | 0
2.60.02. | 2.60 | Procurement, bending, cutting and embedding of smooth reinforcement completely according to the details from The design. Quality of reinforcement S240 (GA 240/360). | kg | 0
2.60.03. | 2.60 | Procurement, bending, cutting and embedding of anchors of deformed bar reinforcement for the connection of the new parapet, in particular according to the details of reinforcement from the Project. The position also includes drilling of holes with diamond drills and grouting with expanding mortar, holes 20 mm in diameter. Quality of reinforcement B500B. | kg | 93.24 |  | 0
2.60.04. | 2.60 | Procurement, bending, cutting and embedding of deformed bar reinforcement completely according to the details from The design for new parapet. Quality of reinforcement B500B. | kg | 22.4 |  | 0
2.60.05. | 2.60 | Procurement, bending, cutting and embedding of mesh reinforcement completely according to the details for covers for installation pos. 2.50.03. Quality of reinforcement B500B. | kg | 140.4 |  | 0
TOTAL FOR POS. 2.60. | [5 empty] | 0
2.70. |  | METALLIC WORKS
2.70.01. | 2.70 | Procurement, making in the workshop, ACP, transport and mounting of two-sided pedestrian path fence on the span part of the bridge. The mounting of the fence is done by welding to the previously mounted steel plates (pos.2.150.03./poz.2.150.4). In this position of the work is included procurement of transport and installation of bolts M20 qu. 8.8 for the connection of the segments of the fence. | m' | 40 |  | 0
2.70.02. | 2.70 | Procurement of material, workmanship in the workshop , ACP, transport and mounting of the new two-sided protective fence on the span part of the bridge. The mounting of these barriers is executed by welding to the fence of the walkway. | m' | 0
2.70.03. | 2.71 2.90 | Procurement, making in the workshop, ACP, transport and mounting of steel gullies vertical elements Ø101.6mm length 48.4 cm. This position of works comprises also the workmanship and mounting of the protective steel caps of the gutters. The works on the superstructure are not included in this position of works (see Pos.2.140). | kom. | 10 |  | 0
2.70.04. | 2.71 2.90 | Procurement of material, workmanship in the workshop , ACP, transport and mounting of the protective barriers on the bridge. The mounting of these barriers is executed by welding to the fence of the walkway. | m' | 0 |  |  | No installation of barriers are foreseen.
2.70.05. | 2.70 2.152 | Procurement of material, workmanship in the workshop, ACP and embedding of pipes Ø30mm , length 27cm for dewatering of installation canals. These small tubules are placed in the previously prepared holes and after the execution of waterproofing of the installation canals. This position of works comprises also a drilling of holes for pipes Ø35mm , as well as the making and mounting of caps for pipes and protective meshes. | kom. | 14 |  | 0
2.70.06. | 2.71 2.90 | Procurement of material, workmanship in the workshop, AKZ, transport and embedding of cover plates for the installation canals of corrugated sheet metal on the places of passing of dilatation couplers. This position of works comprises also the drilling of holes , procurement and embedding of anchor bolts for the fastening of corrugated sheet metal. | kg | 90 |  | 0 | The estimated quantity depends on the choice of the producer. The anker bolts are included in the price.
TOTAL FOR POS. 2.70. | [5 empty] | 0
2.80. |  | WORKS ON REHABILITATION OF CONCRETE SURFACES
2.80.01. | 2.80 | Rehabilitation of the protective layer of concrete . The position of damage is presented in The imaging of damages - mark B.1. It is forseen rehabilitation of the protective layer of concrete on all visible surfaces of the bridge, applying a special mortar for fine profiling with a minimum thickness of 2 mm. This position of works comprises the procurement, transport and embedding of reparative material. | m2 | 329 |  | 0 | It is impossible to ascertain how much of the construction has an insufficient protective layer. Concrete restoration is anticipated on all visible surfaces.
2.80.02. | 2.80 | Rehabilitation of segregated concrete zones. The position of damages is presented in The imaging of damages - mark B.2. This position comprises the procurement , transport and embedding of the reparative material. | m2 | 7.4 |  | 0
2.80.03. | 2.80 | Rehabilitation of mechanical damages of concrete. The damage positions are presented in The imaging of damages - mark B.3. This position comprises the procurement, transport and embedding of the reparative material. | dm3 | 12.25 |  | 0
2.80.04. | 2.80 | Rehabilitation of degraded concrete zones deeper than 5cm. The position of damages is presented in The imaging of damages - mark B.4. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 0.05 |  | 0
2.80.05. | 2.80 | Rehabilitation of degraded concrete zones from 0,5cm-5cm. The position of damage is presented in The imaging of damages - mark B.5. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 40.13 |  | 0
2.80.06. | 2.80 | Rehabilitation of surface degradations of concrete to 0,5cm. The position of damage is presented in The imaging of damages - mark B.6. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 6.54 |  | 0
2.80.07. | 2.80 | Rehabilitation of the zone of extension of concreting. The position of damage is presented in The imaging of damages - mark B.7. and B.8. This position of works comprises the procurement , transport and embedding of reparative material. | m' | 0
2.80.08. | 2.80 | Rehabilitation of calcified concrete zones. The position of damage is presented in The imaging of damages - mark B.9. and B.10. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 0 |  |  | Covered with the position 2.80.01.
2.80.09. | 2.80 | Rehabilitation (injecting-grouting) of fissures to 3mm. The position of damage is presented in The imaging of damages - mark B.11. and B.13. This position of works comprises the procurement , transport and embedding of reparative material. | m' | 0
2.80.10. | 2.80 | Rehabilitation of fissures/cracks bigger than 3mm. The position of damage is presented in The imaging of damages - mark B.12. and B.14. This position of works comprises the procurement , transport and embedding of reparative material. | m' | 0
2.80.11. | 2.80 | Rehabilitation of mesh fissures. The position of damage is presented in The imaging of damages - mark B.15. and B.16. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 0
2.80.12. | 2.80 | Rehabilitation of badly executed local repairs of concrete . The position of damage is presented in The imaging of damages - mark B.17. and P.4. This position of works comprises the procurement , transport and embedding of reparative material. | kom. | 0
2.80.13. | 2.80 | Rehabilitation of the places of anchoring of the preloading cables . The position of damage is presented in The imaging of damages - mark P.3. This position of works comprises the procurements , transport and embedding of reparatory material. | kom. | 0 |  |  | The bridge does not have a prestressing system
2.80.14. | 2.80 | Rehabilitation of the upper surface of the sloping layer below the existing waterproofing and vertical walls of the basin of crushed stone surfacing by reparative materials as a preparation of surfaces for the applying of the new insulation on the basis of MMA. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 25 |  | 0 | Unknown state of the sloping layer. Presumably 25% of the area on which the waterproofing is installed
2.80.15. | 2.80.10 | Applying of the protective layer of concrete on all the visible surfaces with previous preparation of concrete surface by abrasive methods. The paint for the applying of protective coating should be determined in agreement with The supervising body and The investor . The position of works comprises the procurement of materials , transport and applying. Recommendation: SikaGard 680s or coating of similar or better characteristics. | m2 | 329 |  | 0
2.80.16. | 2.80 | making of new sloping layer in the installation canals of reparative mortar in the thicknesses from 0,6 to 1 cm. This position comprises the procurement , transport and embedding of reparative material. | m2 | 8 |  | 0 | The bottom of the canal is made with the slope by the original design, so making of new sloping layer is not needed.
2.80.17. | 2.80 | Rehabilitation of internal surfaces of the installation canals and making of the layer for slopes by reparative materials. This position comprises the procurement , transport and embedding of reparative material as well as the temporary local displacement of the installations. | m2 | 11 |  | 0 | Unknown state of the area on the entire length of the channel. Presumably 25% of the area on which the waterproofing is installed
TOTAL FOR POS. 2.80. | [5 empty] | 0
2.90. |  | WORKS ON ANTI-CORRSION PROTECTION FOR STEEL
2.90.01. | 2.91 | ACP reinforcement on the places damages concrete surfaces. The position of damage is presented in The imaging of damages - mark A.1. and A.2. This position of works comprises the procurement , transport and embedding of reparative material. | m2 | 2 |  | 0 | Unit of measurement is m2 of surface area of damaged reinforcement
2.90.02. | 2.92 | ACP of wires/cables/ribbed pipes for preloading. The position of damage is presented in The imaging of damages - mark P.1. and P.2. This position comprises the procurement , transport and embedding of reparative material. | m2 | 0 |  |  | The bridge does not have a prestressing system
2.90.03. |  | Anti-corrosion protection of other steel elements is included within the positions of works under Pos.70. Metallic works.
TOTAL FOR POS. 2.90. | [5 empty] | 0
2.100. |  | WORKS ON THE WATERPROOFING
2.100.01. | 2.101 | Making of new waterproofing of RC deck on the basis of MMA. The waterproofing is executed on the entire bridge length in full profile with the special details of workmanship in the zone of gutter vertical elements, as well as on the vertical surfaces of crushed stone layer of basin. The position of works comprises the procurement, transport and embedding of waterproofing material. Rehabilitation of the upper surface of roadway RC slab and vertical walls of of the crushed stone basin is given separately in the position of works Pos.2.80.14. The works on the superstructure are not included in this position of works (see Pos.2.140). | m2 | 97 |  | 0
2.100.02. | 2.101 | Making of new waterproofing for installation canals on the basis of MMA. The waterproofing is executed on the entire length of the installation canals in a full profile with special workmanship detail in the zone of aligning surfaces of prefabricated RC cover plates. this position comprises the procurement , transport and embedding of waterproofing material , as well as the temporary displacement of installations. | m2 | 43.6 |  | 0
2.100.03. | 2.101.7 | Making of the waterproofing coating of walking surfaces of the walkways. The coating is executed also over the prefabricated RC cover plates for the installation canals. This position of works comprises the procurement, transport, preparation of surfaces and embedding of waterproofing material with the prior cleaning of the surface by abrasive methods. | m2 | 26 |  | 0
2.100.04. | 2.157 | Protection of waterproofing from damages when installing ballast (crushed stone). Procurement, cutting and placement of panels of extruded polystyrene (styrofoam) 20mm thick. Calculation per m2 of surface protected by new waterproofing of the RC deck. | m2 | 97 |  | 0
TOTAL FOR POS. 2.100. | [5 empty] | 0
2.110. |  | EXPANSION JOINTS, POINTING AND BEARINGS
2.110.01. | 2.112 | Embedding of waterproof dilatation couplers. | m' | 10.8 |  | 0
2.110.02. | 2.113 | Cleaning and sealing of spaces. This position comprises the cleaning, chiselling and opening of joints up to the depth of 5 cm and a permanent sealing of joints by elastic mass. | m' | 0 |  |  | There are no joints on the bridge
2.110.03. | 2.111 | Replacement of existing bearings . | kom. | 0 |  |  | There are no classic bearings on the bridge
TOTAL FOR POS. 2.110. | [5 empty] | 0
2.120. |  | DEWATERING
2.120.01. | 2.120 | Making of the closed dewatering system on the bridge, consisting of the gutter horizontal elements, vertical elements by the columns, collectors and separators. | Completely according to: Book 3 - Hydro technical design.
TOTAL FOR POS. 2.120. | [5 empty] | 0
2.130. |  | INSTALLLATIONS AND POWEER SUPPLY GRID ON THE BRIDGE
2.130.01. | 2.153 | Removal of sand/gravel from the installation channels, and then the cleaning of canals by compressed air. The average thickness of sand/crushed stone that is being removed is 10cm. This position of works comprises also the transport of removed material to the landfill, and the temporary local displacement of the installations. | m3 | 1.6 |  | 0
2.130.02. | 2.130 | Procurement , transport and embedding of sand as the base / protection of the installations . Sand is embedded in two layers - the first layer 5cm thick as the base ( below) and the second layer 5 cm thick as the protection of the installations (above). The total thickness of sand is 10cm. This position comprises the temporary local removal of the installations. | m3 | 1.6 |  | 0
2.130.03. | 2.130 | Dismantling and repeated mounting of the existing cable for the grounding of the power grid overhead contact line (OCL) column on the link with a rail. The bounding cable is joined to the rail by welding. | kom. | 0 |  |  | There are no columns of the contact network on the bridge
2.130.04. | 2.85 | Making of grout below the overhead contact line (OCL) column. The aligning size of steel panel on the joint of pylon for power grid is 60x60cm. This position comprises the procurement , transport and embedding of the material for grouting. | kom. | 0 |  |  | There are no columns of the contact network on the bridge
2.130.05. | 2.82 | Replacement of bad/embedding of missing anchors bolts M30 of a necessary length on the joint of overhead contact line (OCL) column and RC cantilever. The position of these works comprises the procurement, transport and embedding of anchor bolts. NOTE: The work is carried out with the switching off of the voltage in the power supply grid. | kom. | 0 |  |  | There are no columns of the contact network on the bridge
2.130.06. | 2.156 | Securing the workplace from the influence of voltage in the contact network. Immediately after switching off the current which is done by the ZICG, the expert team of the Contractor performs the grounding of the return circuit line on both sides of the bridge with the grounding rods. Calculation by m' of total dismantled track. | m' | 38 |  | 0
TOTAL FOR POS. 2.130. | [5 empty] | 0
2.140. |  | WORKS ON THE SUPERSTRUCTURE FOR THE PURPOSES OF REHABILITATION OF THE BRIDGE
2.140.02 | 2.140.02 | PROCUREMENT OF NEW IMPREGNATED BEECH SLEEPERS OF SIZE 16 x 26 x 260 cm. This position comprise the procurement and delivery to the construction site of new rail track sleepers according to EN13145 of size16 x 26 x 260cm. Calculation and payment per piece of delivered sleepers. | pcs. | 64 |  | 0
2.140.03 | 2.140.03 | PROCUREMENT OF NEW FASTENING ACCESSORY TYPE "K" FOR A WOODEN SLEEPER, DRIVING AND SAFETY RAILS 49E1 . This position comprises the procurement and delivery to the construction site of the complete new fastening accessory type "K" for wooden sleepers and rails 49E1. One set contains: processed ribbed washer plate - 2 pieces, tirfon - 8 pcs, twofold elastic ring washer - 12 pieces, bolt of "T" shape together with a nut - 4 pieces, fastening plate - 4 pcs, rubber insert - 2 pcs. The calculation and payment by a set of delivered fastening accessory per sleeper. | set | 64 |  | 0
2.140.04 | 2.140.04 | PROCUREMENT, EXTERNAL TRANSPORT AND UNLOADING OF CRUSHED STONE OF LIMESTONE ORIGIN. This position comprises the procurement, external transport and unloading on the place of embedding of crushed stone in Fed trolleys, with grain-size according to the standard for reception and delivery of crushed stone for the surfacing of railway lines. The calculation and payment for m3 of delivered crushed stone. | m³ | 83 |  | 0
2.140.05 | 2.140.05 | PROCUREMENT OF SETS FOR THE WELDING OF RAIL TRACK IN LRT OF 49E1 RAILS. This position comprises the procurement of all the necessary material for the making of welds on rail track made of 49E1 rails in LRT. The calculation and payment by a set. | complete | 10 |  | 0
2.140.06 | 2.140.06 | PROCUREMENT OF UTENSILS AGAINST THE LONGITUDINAL RAIL DISPLACEMENTS . This position comprises the procurement and delivery of the utensils to the building site. The calculation and payment by a piece of delivered utensils.
|  | for wooden sleepers | pcs. | 148 |  | 0
2.140.07 | 2.140.07 | PROCUREMENT OF THE UTENSILS AGAINST THE LATERAL RAIL TRACK DISPLACEMENT. This position comprises the procurement and delivery of utensils on the building site.. The calculation and payment by a piece of delivered utensils.
|  | for wooden sleepers | kom | 22 |  | 0
2.140.09 | 2.140.09 | UNLOADING OF IMPREGNATD WOODEN SLEEPERS OF SIZE 16 x 26 x 260 cm. This position comprises the unloading of sleepers from trolleys, transfer to the construction site landfill and arrangement. The calculation and payment per piece of unloaded sleepers. | pcs. | 64 |  | 0
2.140.10 | 2.140.10 | UNLOADING OF TIGHTENING ACCESSORY TYPE „K“. This position comprises the unloading of rail track fastening accessory from trolleys with the transfer and arraigning in the construction site storeroom. The calculation and payment per ton of unloaded accessory. | t | 1.64 |  | 0
2.140.11 | 2.140.11 | UNLOADING OF UTENSILS AGAINST LONGITUDINAL RAIL DISPLACEMENTS. This position comprises an unloading of the utensils against a longitudinal rail displacement. The calculation and payment by a piece of unloaded utensils.. | pcs. | 148 |  | 0
2.140.12 | 2.140.12 | UNLOADING OF DEVICES AGAINST LATERAL TRACK RAIL DIPLACEMENTS. This position comprises an unloading of the utensils. The calculation and payment by a piece of unloaded utensils. | pcs. | 22 |  | 0
2.140.13 | 2.140.13 | DISMANTLING OF THE EXISTING RAIL TRACK. This position comprises a dismantling of the existing rail track, as well as the dismantling of the safety rails, with loading, transport to 10 km , unloading, dismantling and arranging by type and serviceability level. The calculation and payment by a km of dismantled rail track. | km | 0.038 |  | 0
2.140.14 | 2.140.14 | REMOVAL OF THE EXISTING CRUSHED STONE SURFACING LAYER. This position comprises the complete cleaning and removal of the existing crushed stone surfacing layer with all accompanying works, below the rail track mesh on the bridge, to the existing railway slab of the bridge, with loading, transport to 10 km and unloading on the landfill. The calculation and payment by m3 of removed surfacing. | m³ | 69 |  | 0
2.140.15 | 2.140.15 | MOUNTING AND LAYING OF RAIL TRACK OF RAILS TYPE 49E1 ON WOODEN SLEEPERS. This position comprises the mounting and laying of rail track in front of and behind the bridge, on wooden sleepers, with the fastening accessory type "K". The calculation and payment by a km of the installed rail track. | km | 0.02 |  | 0
2.140.16 | 2.140.16 | MOUNTING AND LAYING OF THE RAIL TRACK OF RAILS TYPE 49E1 ON WOODEN SLEEPERS ON THE BRIDGE. This position comprises the mounting an laying of rail track on the bridge , on wooden sleepers, by a fastening accessory type "K". The calculation and payment by a km of mounted and installed rail track. . | km | 0.018 |  | 0
2.140.22 | 2.140.22 | MECHANICAL ADJUSTMENT AND DYNAMIC STABILIZING OF RAIL TRACK OF RAILS TYPE 49E1. This position comprises the embedding of crushed stone in the rail track, raising of the rail track on the finished road level with a necessary camber and extensions in curvatures and under-compacting, mechanical regulating of the rail track by a direction and finished road level, fastening by proper accessory of rails type 49E1 with setting of the ballast prism (surfacing layer) and maintenance to the handover. The calculation and payment by a km of finally regulated rail track settled in the designed position. | km | 0.038 |  | 0
2.140.23 | 2.140.23 | WELDING OF RAIL TRACK OF RAILS TYPE 49E1 IN LRT BY AT PROCESS . This position comprises the welding of the rail track of rails type 49E1 in LRT by AT process, with the processing of welds and provisions of attests of the quality of welds. The calculation and payment by a weld. | weld | 10 |  | 0
2.140.24 | 2.140.24 | RELEASE OF STRESS IN RAILS TYPE 49E1 WITH A FINAL WELDING. This position comprises the release of stress in the rails with a final welding according to The rulebook of the superstructure maintenance on the rail tracks. The calculation and payment by a km of released rail track. | km | 0.038 |  | 0
2.140.25 | 2.140.25 | EMBEDDING OF THE UTENSILS AGAINST A LONGITUDINAL RAIL DISPLACEMENT (MATHEE). This position comprises the embedding of utensils against a longitudinal rail displacement. The calculation and payment by a piece of the utensils. | pcs. | 148 |  | 0
2.140.26 | 2.140.26 | EMBEDDING OF UTENSILS AGAINST LATERAL RAIL DISPLACEMENT. This position comprises the embedding of utensils against lateral rail displacements. The calculation and payment by a piece of utensils. | pcs. | 22 |  | 0
2.140.27 | 2.140.27 | ADDITIONAL WORKS ON THE BRIDGE SUPERSTRUCTURE FOR THE EMBEDDING OF NEW WATERPROOFING, NEW GUTTER ELEMENTS AN DNEW BRIDGE DILATATIONS. This position comprises the necessary additional works on the bridge superstructure , such as: - cutting of the existing rail track in sections of 22,50 m, where a length on the embankment of 10,00m from the abutments ,in front of an behind the bridge, is taken into account; - dismantling of rail tracks in segments , with a temporary removal; - temporary mounting of the rail track , with drilling of rails , mounting of fastening links and necessary track accessory; - dismantling of rail content before welding of rails; This position comprises the procurement , transport and embedding of used elements for rails type 49E1. On complete consists of : link with rail type 49E1 for a joint - 2 pcs. bolt for joints M24 x 400 for one joint - 2 pcs. hexagonal nut for bolts for links M24 for one joint - 2 pcs. twofold elastic ring washer (Grower ring) - 2 pcs. The calculation and payment by a piece of joint. | pcs. | 6 |  | 0
TOTAL FOR POS. 2.140. | [5 empty] | 0
2.150. |  | OTHER WORKS
2.150.01. | 2.71 2.90 | Embedding of steel panels for link of the fence of walkway. The steel panels are jointed to the structure by the anchor bolts M12, length 15cm, 4 pcs.. This position comprises the procurement of materials, workmanship, transport and mounting. | pcs. | 22 |  | 0
2.150.02 | 2.152 | Embedding of anchor bolts HST-R M12, lenght 15cm for link of of steel panels of the fence of walkway and concreete of the walkaway path console (4 pcs per plate). This position comprises the procurement of materials, transport drilling of holes Ø13mm and embedding of anchor bolts. | pcs. | 88 |  |  | Price covered by the position 2.150.01
2.150.03 | 2.80 | Making of new drip cap on the cantilevers of columns of electrification by "cutting grips" the concrete console. | m' | 0 |  |  | There is no cantilevers of electrified columns on the bridge
2.150.04 |  | Creation of a support during the execution of works for the insurance of the construction works zone. | pcs. | 1 |  |  | According to the contractor's design.
TOTAL FOR POS. 2.150. | [5 empty] | 0
2.160. |  | CONSULTING SERVICES
2.160.01. |  | The designer's supervision during the execution of works on the rehabilitation. Consulting services for the main project's modifications and supplements and the occasional presence on the facility to control the key positions of the works. The scope of engagement defines the Employer's Supervision according to real needs. | lump sum | 1 |  | 4500 | P.S.*
2.160.02. |  | The Investor's supervision during the execution of works on the rehabilitation. (N/A FIDIC Engineer defined in the Appendix to Tender) | lump sum | 0
2.160.03. |  | Creating As - Built Design (part of the Facility Maintenance Project) | lump sum | 1
2.160.04. |  | Commission for the technical accept of the facility. | lump sum | 1 |  | 5000 | P.S.*
TOTAL FOR POS. 2.160. | [5 empty] | 9500
TOTAL FOR ALL THE WORKS | [5 empty] | 9500
NOTES: - All works mentioned in the estimate are executed completely according to the Graphic documentation from the Design , as well as the Technical specifications for the execution of works given in the Design. - Quantities Pos. 2.80. The works on the rehabilitation of concrete surfaces are given according to the Report on the state of the bridge from 2015.
* P.S - To be paid as per Sub-Clause 13.5 - Provisional Sums